## DISTRIBUTION
Module Code | Module Description | ClickUp Task Count | System Weight Allocation | Actual Accomplishment
MOD-FE | Frontend User Interface | 20 | 24.5% | 0%
MOD-BE | Backend and API Services | 16 | 23.5% | 0%
MOD-DB | Database, ETL, and Storage Layers | 10 | 8% | 0%
MOD-ANA | Analytics, Models, and Decision Support | 6 | 28.5% | 0%
CORE | Hosting, Repository, and Project Management | 2 | 5.5% | 0%
MANUSCRIPT | Manuscript and Documentation | 6 | 10% | 0%
TOTAL | PAULUS Project Scope | 60 | 100% | 0%

## MOD-FE
Task ID | LOGIN | Task Name | Login and User Access Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tg64
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define login interface requirements | Given the PAULUS Define login interface requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define login interface requirements. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mdr
DES-01 | Design login page wireframe | Given the PAULUS Design login page wireframe task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design login page wireframe. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mgb
DEV-01 | Build login page layout | Given the PAULUS Build login page layout task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build login page layout. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mke
DEV-02 | Connect login form to authentication API | Given the PAULUS Connect login form to authentication API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Connect login form to authentication API. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mp8
TEST-01 | Test valid and invalid login behavior | Given the PAULUS Test valid and invalid login behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test valid and invalid login behavior. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mrn
FIX-01 | Resolve login form and validation issues | Given the PAULUS Resolve login form and validation issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve login form and validation issues. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390muz
UAT-01 | Validate login process with target users | Given the PAULUS Validate login process with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate login process with target users. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390mxy
MS-01 | Document login interface in Chapter 4 | Given the PAULUS Document login interface in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document login interface in Chapter 4. | 0.1531% | planning/backlog | FALSE | https://app.clickup.com/t/86d390n0p
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | DASH | Task Name | Main Financial Dashboard |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tg6m
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define dashboard data and filter requirements | Given the PAULUS Define dashboard data and filter requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define dashboard data and filter requirements. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390n52
DES-01 | Create dashboard wireframe | Given the PAULUS Create dashboard wireframe task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Create dashboard wireframe. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390nvz
DEV-01 | Build dashboard layout components | Given the PAULUS Build dashboard layout components task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build dashboard layout components. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390p6m
DEV-02 | Add financial summary cards | Given the PAULUS Add financial summary cards task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Add financial summary cards. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390p8g
DEV-03 | Add chart and visualization components | Given the PAULUS Add chart and visualization components task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Add chart and visualization components. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pb0
DEV-04 | Connect dashboard to backend API data | Given the PAULUS Connect dashboard to backend API data task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Connect dashboard to backend API data. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pde
TEST-01 | Verify dashboard data rendering and filters | Given the PAULUS Verify dashboard data rendering and filters task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Verify dashboard data rendering and filters. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pfw
FIX-01 | Resolve dashboard display and calculation issues | Given the PAULUS Resolve dashboard display and calculation issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve dashboard display and calculation issues. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pjm
UAT-01 | Validate dashboard usability with target users | Given the PAULUS Validate dashboard usability with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate dashboard usability with target users. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pn2
MS-01 | Document dashboard module in Chapter 4 | Given the PAULUS Document dashboard module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document dashboard module in Chapter 4. | 0.1225% | planning/backlog | FALSE | https://app.clickup.com/t/86d390pqg
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | INST | Task Name | Institution Management Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tg8j
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define institution management requirements | Given the PAULUS Define institution management requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define institution management requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design institution management interface and workflow | Given the PAULUS Design institution management interface and workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design institution management interface and workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build institution management interface | Given the PAULUS Build institution management interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build institution management interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test institution create, update, view, and validation behavior | Given the PAULUS Test institution create, update, view, and validation behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test institution create, update, view, and validation behavior. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve institution management issues | Given the PAULUS Resolve institution management issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve institution management issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate institution management with target users | Given the PAULUS Validate institution management with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate institution management with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document institution management module in Chapter 4 | Given the PAULUS Document institution management module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document institution management module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | TWIN | Task Name | Digital Twin Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgck
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
TWIN | Digital Twin Interface | Given the PAULUS Digital Twin Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Digital Twin Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgck
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | WHATIF | Task Name | What-If Simulator Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgd8
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define what-if simulator requirements | Given the PAULUS Define what-if simulator requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define what-if simulator requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design what-if simulator input and output workflow | Given the PAULUS Design what-if simulator input and output workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design what-if simulator input and output workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build what-if simulator interface | Given the PAULUS Build what-if simulator interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build what-if simulator interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test scenario input, calculation display, and reset behavior | Given the PAULUS Test scenario input, calculation display, and reset behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test scenario input, calculation display, and reset behavior. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve what-if simulator issues | Given the PAULUS Resolve what-if simulator issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve what-if simulator issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate what-if simulator with target users | Given the PAULUS Validate what-if simulator with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate what-if simulator with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document what-if simulator module in Chapter 4 | Given the PAULUS Document what-if simulator module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document what-if simulator module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | BUDGET | Task Name | Budget Page |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6fq
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define budget page requirements | Given the PAULUS Define budget page requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define budget page requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design budget page interface and workflow | Given the PAULUS Design budget page interface and workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design budget page interface and workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build budget page interface | Given the PAULUS Build budget page interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build budget page interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test budget page display, totals, filters, and validation | Given the PAULUS Test budget page display, totals, filters, and validation task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test budget page display, totals, filters, and validation. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve budget page issues | Given the PAULUS Resolve budget page issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve budget page issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate budget page with target users | Given the PAULUS Validate budget page with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate budget page with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document budget page module in Chapter 4 | Given the PAULUS Document budget page module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document budget page module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | EVENTS | Task Name | Events Page |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6gu
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define events page requirements | Given the PAULUS Define events page requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define events page requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design events page interface and calendar workflow | Given the PAULUS Design events page interface and calendar workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design events page interface and calendar workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build events page interface | Given the PAULUS Build events page interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build events page interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test event creation, editing, viewing, filtering, and validation | Given the PAULUS Test event creation, editing, viewing, filtering, and validation task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test event creation, editing, viewing, filtering, and validation. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve events page issues | Given the PAULUS Resolve events page issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve events page issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate events page with target users | Given the PAULUS Validate events page with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate events page with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document events page module in Chapter 4 | Given the PAULUS Document events page module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document events page module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | REPORT | Task Name | Report Viewing and Export Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgc8
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REPORT | Report Viewing and Export Interface | Given the PAULUS Report Viewing and Export Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Report Viewing and Export Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgc8
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | GEO | Task Name | Geospatial Institution Map |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tged
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
GEO | Geospatial Institution Map | Given the PAULUS Geospatial Institution Map task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Geospatial Institution Map. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tged
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | PRST | Task Name | Priest Health Tracker Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgmg
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
PRST | Priest Health Tracker Interface | Given the PAULUS Priest Health Tracker Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Priest Health Tracker Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgmg
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | PROJ | Task Name | Projects and Donations Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgb5
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define projects and donations page requirements | Given the PAULUS Define projects and donations page requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define projects and donations page requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design projects and donations interface workflow | Given the PAULUS Design projects and donations interface workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design projects and donations interface workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build projects and donations page interface | Given the PAULUS Build projects and donations page interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build projects and donations page interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test project listing, detail, donation display, and validation behavior | Given the PAULUS Test project listing, detail, donation display, and validation behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test project listing, detail, donation display, and validation behavior. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve projects and donations page issues | Given the PAULUS Resolve projects and donations page issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve projects and donations page issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate projects and donations page with target users | Given the PAULUS Validate projects and donations page with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate projects and donations page with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document projects and donations module in Chapter 4 | Given the PAULUS Document projects and donations module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document projects and donations module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | CHAT | Task Name | AI Chatbot Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgkb
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
CHAT | AI Chatbot Interface | Given the PAULUS AI Chatbot Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for AI Chatbot Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgkb
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | ANALYTICS | Task Name | Analytics and Decision-Support |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgbx
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
ANALYTICS | Analytics and Decision-Support | Given the PAULUS Analytics and Decision-Support task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Analytics and Decision-Support. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgbx
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | FS | Task Name | Financial Statement Upload Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgaq
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
FS | Financial Statement Upload Interface | Given the PAULUS Financial Statement Upload Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Financial Statement Upload Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgaq
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | ANNC | Task Name | Announcements Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgbu
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define announcements page requirements | Given the PAULUS Define announcements page requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define announcements page requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design announcements page and notification display | Given the PAULUS Design announcements page and notification display task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design announcements page and notification display. | 0.175% | planning/backlog | FALSE | https://app.clickup.com/t/86d390g9n
DEV-01 | Build announcements page interface | Given the PAULUS Build announcements page interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build announcements page interface. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test announcement creation, editing, publishing, and display | Given the PAULUS Test announcement creation, editing, publishing, and display task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test announcement creation, editing, publishing, and display. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve announcements page issues | Given the PAULUS Resolve announcements page issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve announcements page issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate announcements page with target users | Given the PAULUS Validate announcements page with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate announcements page with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document announcements module in Chapter 4 | Given the PAULUS Document announcements module in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document announcements module in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | NOTIF | Task Name | Notification Feature |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6ht
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define notification UI requirements | Given the PAULUS Define notification UI requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define notification UI requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design notification display and read-state workflow | Given the PAULUS Design notification display and read-state workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design notification display and read-state workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build notification display and read-state UI | Given the PAULUS Build notification display and read-state UI task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build notification display and read-state UI. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test notification visibility, dismissal, and state behavior | Given the PAULUS Test notification visibility, dismissal, and state behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test notification visibility, dismissal, and state behavior. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve notification UI issues | Given the PAULUS Resolve notification UI issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve notification UI issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate notifications with target users | Given the PAULUS Validate notifications with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate notifications with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document notification feature in Chapter 4 | Given the PAULUS Document notification feature in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document notification feature in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | IAFR | Task Name | IAFR Data Entry and Upload Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tga9
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
IAFR | IAFR Data Entry and Upload Interface | Given the PAULUS IAFR Data Entry and Upload Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for IAFR Data Entry and Upload Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tga9
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | AUDITLOG | Task Name | Audit Log Viewing Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgxt
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
AUDITLOG | Audit Log Viewing Interface | Given the PAULUS Audit Log Viewing Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Audit Log Viewing Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgxt
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | ADMIN | Task Name | Admin Management Interface |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tgy3
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
ADMIN | Admin Management Interface | Given the PAULUS Admin Management Interface task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Admin Management Interface. | 1.225% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tgy3
Total Accomplished |  |  |  | 1.225% |  | 0%
Task ID | ARCHIVES | Task Name | Archives Page / Archive Management |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6jy
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define archive UI requirements | Given the PAULUS Define archive UI requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define archive UI requirements. | 0.175% | standardized subtask - URL pending | FALSE
DES-01 | Design archive listing and restore workflow | Given the PAULUS Design archive listing and restore workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design archive listing and restore workflow. | 0.175% | standardized subtask - URL pending | FALSE
DEV-01 | Build archive listing and restore controls | Given the PAULUS Build archive listing and restore controls task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build archive listing and restore controls. | 0.175% | standardized subtask - URL pending | FALSE
TEST-01 | Test archive and restore workflows for supported records | Given the PAULUS Test archive and restore workflows for supported records task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test archive and restore workflows for supported records. | 0.175% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve archive management UI issues | Given the PAULUS Resolve archive management UI issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve archive management UI issues. | 0.175% | standardized subtask - URL pending | FALSE
UAT-01 | Validate archive workflows with target users | Given the PAULUS Validate archive workflows with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate archive workflows with target users. | 0.175% | standardized subtask - URL pending | FALSE
MS-01 | Document archive management feature in Chapter 4 | Given the PAULUS Document archive management feature in Chapter 4 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document archive management feature in Chapter 4. | 0.175% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.225% |  | 0%
Module Accomplishment | MOD-FE | Frontend User Interface |  | 24.5% |  | 0%

## MOD-BE
Task ID | AUTH | Task Name | Authentication and Role Access API |  | in progress |  | https://app.clickup.com/t/86d38tft1
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define authentication and role access requirements | Given the PAULUS Define authentication and role access requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define authentication and role access requirements. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901rz
DES-01 | Create authentication flow diagram | Given the PAULUS Create authentication flow diagram task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Create authentication flow diagram. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901tv
DEV-01 | Implement login endpoint | Given the PAULUS Implement login endpoint task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Implement login endpoint. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901up
DEV-02 | Implement logout and session handling | Given the PAULUS Implement logout and session handling task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Implement logout and session handling. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901vx
DEV-03 | Implement role-based access control | Given the PAULUS Implement role-based access control task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Implement role-based access control. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901ww
TEST-01 | Test valid and invalid authentication attempts | Given the PAULUS Test valid and invalid authentication attempts task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test valid and invalid authentication attempts. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901xz
FIX-01 | Resolve authentication and session issues | Given the PAULUS Resolve authentication and session issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve authentication and session issues. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d3901yk
UAT-01 | Validate user access based on assigned roles | Given the PAULUS Validate user access based on assigned roles task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate user access based on assigned roles. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d390202
MS-01 | Document authentication and role access process | Given the PAULUS Document authentication and role access process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document authentication and role access process. | 0.1632% | planning/backlog | FALSE | https://app.clickup.com/t/86d390213
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | INSTAPI | Task Name | Institution Management API |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tfth
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
INSTAPI | Institution Management API | Given the PAULUS Institution Management API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Institution Management API. | 1.469% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tfth
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | PROJAPI | Task Name | Projects and Donations API |  | in progress |  | https://app.clickup.com/t/86d38tfuf
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
PROJAPI | Projects and Donations API | Given the PAULUS Projects and Donations API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Projects and Donations API. | 1.469% | in progress | FALSE | https://app.clickup.com/t/86d38tfuf
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | ANNCAPI | Task Name | Announcements API |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tfuw
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
ANNCAPI | Announcements API | Given the PAULUS Announcements API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Announcements API. | 1.469% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d38tfuw
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | FSAPI | Task Name | Financial Statement Processing API |  | planning/backlog |  | https://app.clickup.com/t/86d38tfu2
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
FSAPI | Financial Statement Processing API | Given the PAULUS Financial Statement Processing API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Financial Statement Processing API. | 1.469% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tfu2
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | IAFRAPI | Task Name | IAFR Processing API |  | planning/backlog |  | https://app.clickup.com/t/86d38tftn
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
IAFRAPI | IAFR Processing API | Given the PAULUS IAFR Processing API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for IAFR Processing API. | 1.469% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tftn
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | ANALYTICSAPI | Task Name | Analytics Result API |  | planning/backlog |  | https://app.clickup.com/t/86d38tg0q
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
ANALYTICSAPI | Analytics Result API | Given the PAULUS Analytics Result API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Analytics Result API. | 1.469% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg0q
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | REPORTAPI | Task Name | Report Generation API |  | planning/backlog |  | https://app.clickup.com/t/86d38tg14
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REPORTAPI | Report Generation API | Given the PAULUS Report Generation API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Report Generation API. | 1.469% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg14
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | BUDGETAPI | Task Name | Budget API and Validation |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6g7
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define budget API requirements | Given the PAULUS Define budget API requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define budget API requirements. | 0.2098% | standardized subtask - URL pending | FALSE
DES-01 | Design budget API request, response, and validation structure | Given the PAULUS Design budget API request, response, and validation structure task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design budget API request, response, and validation structure. | 0.2098% | standardized subtask - URL pending | FALSE
DEV-01 | Build budget API endpoints | Given the PAULUS Build budget API endpoints task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build budget API endpoints. | 0.2098% | standardized subtask - URL pending | FALSE
TEST-01 | Test budget API validation and responses | Given the PAULUS Test budget API validation and responses task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test budget API validation and responses. | 0.2098% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve budget API issues | Given the PAULUS Resolve budget API issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve budget API issues. | 0.2098% | standardized subtask - URL pending | FALSE
UAT-01 | Validate budget API with frontend workflow | Given the PAULUS Validate budget API with frontend workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate budget API with frontend workflow. | 0.2098% | standardized subtask - URL pending | FALSE
MS-01 | Document budget API process | Given the PAULUS Document budget API process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document budget API process. | 0.2098% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | EVENTAPI | Task Name | Events API |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6hb
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define events API requirements | Given the PAULUS Define events API requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define events API requirements. | 0.2098% | standardized subtask - URL pending | FALSE
DES-01 | Design event API request, response, and validation structure | Given the PAULUS Design event API request, response, and validation structure task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design event API request, response, and validation structure. | 0.2098% | standardized subtask - URL pending | FALSE
DEV-01 | Build event CRUD endpoints | Given the PAULUS Build event CRUD endpoints task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build event CRUD endpoints. | 0.2098% | standardized subtask - URL pending | FALSE
TEST-01 | Test event API validation and persistence | Given the PAULUS Test event API validation and persistence task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test event API validation and persistence. | 0.2098% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve events API issues | Given the PAULUS Resolve events API issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve events API issues. | 0.2098% | standardized subtask - URL pending | FALSE
UAT-01 | Validate events API with frontend workflow | Given the PAULUS Validate events API with frontend workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate events API with frontend workflow. | 0.2098% | standardized subtask - URL pending | FALSE
MS-01 | Document events API process | Given the PAULUS Document events API process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document events API process. | 0.2098% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | NOTIFAPI | Task Name | Notification API and Read-State Logic |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6ja
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define notification API requirements | Given the PAULUS Define notification API requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define notification API requirements. | 0.2098% | standardized subtask - URL pending | FALSE
DES-01 | Design notification generation and read-state API flow | Given the PAULUS Design notification generation and read-state API flow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design notification generation and read-state API flow. | 0.2098% | standardized subtask - URL pending | FALSE
DEV-01 | Build notification generation and retrieval logic | Given the PAULUS Build notification generation and retrieval logic task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build notification generation and retrieval logic. | 0.2098% | standardized subtask - URL pending | FALSE
TEST-01 | Test notification targeting and read-state updates | Given the PAULUS Test notification targeting and read-state updates task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test notification targeting and read-state updates. | 0.2098% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve notification API issues | Given the PAULUS Resolve notification API issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve notification API issues. | 0.2098% | standardized subtask - URL pending | FALSE
UAT-01 | Validate notification API with frontend workflow | Given the PAULUS Validate notification API with frontend workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate notification API with frontend workflow. | 0.2098% | standardized subtask - URL pending | FALSE
MS-01 | Document notification API process | Given the PAULUS Document notification API process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document notification API process. | 0.2098% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | ARCHIVEAPI | Task Name | Archive and Restore API |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6kh
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define archive API requirements | Given the PAULUS Define archive API requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define archive API requirements. | 0.2098% | standardized subtask - URL pending | FALSE
DES-01 | Design archive and restore API flow | Given the PAULUS Design archive and restore API flow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design archive and restore API flow. | 0.2098% | standardized subtask - URL pending | FALSE
DEV-01 | Build archive and restore API logic | Given the PAULUS Build archive and restore API logic task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build archive and restore API logic. | 0.2098% | standardized subtask - URL pending | FALSE
TEST-01 | Test archive permissions and restore behavior | Given the PAULUS Test archive permissions and restore behavior task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test archive permissions and restore behavior. | 0.2098% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve archive API issues | Given the PAULUS Resolve archive API issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve archive API issues. | 0.2098% | standardized subtask - URL pending | FALSE
UAT-01 | Validate archive API with frontend workflow | Given the PAULUS Validate archive API with frontend workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate archive API with frontend workflow. | 0.2098% | standardized subtask - URL pending | FALSE
MS-01 | Document archive API process | Given the PAULUS Document archive API process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document archive API process. | 0.2098% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | FINBACKUPAPI | Task Name | Financial Backup Input API |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6rv
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define financial backup input API requirements | Given the PAULUS Define financial backup input API requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define financial backup input API requirements. | 0.2098% | standardized subtask - URL pending | FALSE
DES-01 | Design backup upload and import endpoint flow | Given the PAULUS Design backup upload and import endpoint flow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design backup upload and import endpoint flow. | 0.2098% | standardized subtask - URL pending | FALSE
DEV-01 | Build backup upload and import endpoint | Given the PAULUS Build backup upload and import endpoint task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build backup upload and import endpoint. | 0.2098% | standardized subtask - URL pending | FALSE
TEST-01 | Test import errors, duplicates, and validation | Given the PAULUS Test import errors, duplicates, and validation task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test import errors, duplicates, and validation. | 0.2098% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve financial backup API issues | Given the PAULUS Resolve financial backup API issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve financial backup API issues. | 0.2098% | standardized subtask - URL pending | FALSE
UAT-01 | Validate financial backup API with upload workflow | Given the PAULUS Validate financial backup API with upload workflow task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate financial backup API with upload workflow. | 0.2098% | standardized subtask - URL pending | FALSE
MS-01 | Document financial backup input API process | Given the PAULUS Document financial backup input API process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document financial backup input API process. | 0.2098% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | CHATAPI | Task Name | AI Chatbot API |  | planning/backlog |  | https://app.clickup.com/t/86d38tg1f
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
CHATAPI | AI Chatbot API | Given the PAULUS AI Chatbot API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for AI Chatbot API. | 1.469% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg1f
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | PRSTAPI | Task Name | Priest Health Records API |  | in progress |  | https://app.clickup.com/t/86d38tg03
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
PRSTAPI | Priest Health Records API | Given the PAULUS Priest Health Records API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Priest Health Records API. | 1.469% | in progress | FALSE | https://app.clickup.com/t/86d38tg03
Total Accomplished |  |  |  | 1.469% |  | 0%
Task ID | AUDIT | Task Name | Audit Trail and Activity Log API |  | ready for work |  | https://app.clickup.com/t/86d38tg1r
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
AUDIT | Audit Trail and Activity Log API | Given the PAULUS Audit Trail and Activity Log API task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Audit Trail and Activity Log API. | 1.469% | ready for work | FALSE | https://app.clickup.com/t/86d38tg1r
Total Accomplished |  |  |  | 1.469% |  | 0%
Module Accomplishment | MOD-BE | Backend and API Services |  | 23.5% |  | 0%

## MOD-DB
Task ID | USERDB | Task Name | User and Role Tables |  | in progress |  | https://app.clickup.com/t/86d38tf0b
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
USERDB | User and Role Tables | Given the PAULUS User and Role Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for User and Role Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf0b
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | INSTDB | Task Name | Institution Tables |  | in progress |  | https://app.clickup.com/t/86d38tf2u
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
INSTDB | Institution Tables | Given the PAULUS Institution Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Institution Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf2u
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | IAFRDB | Task Name | IAFR Data Tables |  | in progress |  | https://app.clickup.com/t/86d38tf3c
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
IAFRDB | IAFR Data Tables | Given the PAULUS IAFR Data Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for IAFR Data Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf3c
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | FSDB | Task Name | Financial Statement Tables |  | in progress |  | https://app.clickup.com/t/86d38tf7g
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
FSDB | Financial Statement Tables | Given the PAULUS Financial Statement Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Financial Statement Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf7g
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | PROJDB | Task Name | Projects and Donations Tables |  | in progress |  | https://app.clickup.com/t/86d38tf81
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
PROJDB | Projects and Donations Tables | Given the PAULUS Projects and Donations Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Projects and Donations Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf81
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | PRSTDB | Task Name | Priest Health Records Table |  | in progress |  | https://app.clickup.com/t/86d38tf96
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
PRSTDB | Priest Health Records Table | Given the PAULUS Priest Health Records Table task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Priest Health Records Table. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf96
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | ANALYTICSDB | Task Name | Analytics Output Tables |  | in progress |  | https://app.clickup.com/t/86d38tf9g
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
ANALYTICSDB | Analytics Output Tables | Given the PAULUS Analytics Output Tables task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Analytics Output Tables. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tf9g
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | SANDBOX | Task Name | Sandbox and Model Testing Schema |  | in progress |  | https://app.clickup.com/t/86d38tfat
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
SANDBOX | Sandbox and Model Testing Schema | Given the PAULUS Sandbox and Model Testing Schema task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Sandbox and Model Testing Schema. | 0.8% | in progress | FALSE | https://app.clickup.com/t/86d38tfat
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | BACKUP | Task Name | Backup and Recovery Setup |  | planning/backlog |  | https://app.clickup.com/t/86d38tfcn
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
BACKUP | Backup and Recovery Setup | Given the PAULUS Backup and Recovery Setup task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Backup and Recovery Setup. | 0.8% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tfcn
Total Accomplished |  |  |  | 0.8% |  | 0%
Task ID | FINBACKUP | Task Name | Backup Input for Financial Data |  | planning/backlog |  | https://app.clickup.com/t/86d3bw6t9
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
REQ-01 | Define backup input data requirements | Given the PAULUS Define backup input data requirements task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define backup input data requirements. | 0.1333% | standardized subtask - URL pending | FALSE
DES-01 | Design backup input storage and staging structure | Given the PAULUS Design backup input storage and staging structure task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Design backup input storage and staging structure. | 0.1333% | standardized subtask - URL pending | FALSE
DEV-01 | Build backup input storage and staging structure | Given the PAULUS Build backup input storage and staging structure task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build backup input storage and staging structure. | 0.1333% | standardized subtask - URL pending | FALSE
TEST-01 | Test duplicate handling, validation rules, and import constraints | Given the PAULUS Test duplicate handling, validation rules, and import constraints task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Test duplicate handling, validation rules, and import constraints. | 0.1333% | standardized subtask - URL pending | FALSE
FIX-01 | Resolve financial backup input storage issues | Given the PAULUS Resolve financial backup input storage issues task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Resolve financial backup input storage issues. | 0.1333% | standardized subtask - URL pending | FALSE
MS-01 | Document financial backup input storage design | Given the PAULUS Document financial backup input storage design task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document financial backup input storage design. | 0.1333% | standardized subtask - URL pending | FALSE
Total Accomplished |  |  |  | 0.8% |  | 0%
Module Accomplishment | MOD-DB | Database, ETL, and Storage Layers |  | 8% |  | 0%

## MOD-ANA
Task ID | RATIO | Task Name | Financial Ratio Analysis Module |  | planning/backlog |  | https://app.clickup.com/t/86d38tg2f
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
RATIO | Financial Ratio Analysis Module | Given the PAULUS Financial Ratio Analysis Module task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Financial Ratio Analysis Module. | 4.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg2f
Total Accomplished |  |  |  | 4.75% |  | 0%
Task ID | HEALTH | Task Name | Financial Health Classification Model |  | planning/backlog |  | https://app.clickup.com/t/86d38tg2t
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
HEALTH | Financial Health Classification Model | Given the PAULUS Financial Health Classification Model task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Financial Health Classification Model. | 4.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg2t
Total Accomplished |  |  |  | 4.75% |  | 0%
Task ID | FORECAST | Task Name | Short-Term Financial Forecasting |  | planning/backlog |  | https://app.clickup.com/t/86d38tg3g
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
FORECAST | Short-Term Financial Forecasting | Given the PAULUS Short-Term Financial Forecasting task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Short-Term Financial Forecasting. | 4.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg3g
Total Accomplished |  |  |  | 4.75% |  | 0%
Task ID | RECO | Task Name | Decision-Support Recommendation Model |  | planning/backlog |  | https://app.clickup.com/t/86d38tg4b
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
RECO | Decision-Support Recommendation Model | Given the PAULUS Decision-Support Recommendation Model task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Decision-Support Recommendation Model. | 4.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38tg4b
Total Accomplished |  |  |  | 4.75% |  | 0%
Task ID | LITCAL | Task Name | Liturgical Calendar Data Pipeline |  | for qa / internal testing |  | https://app.clickup.com/t/86d38tg4j
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
BUS-01 | Define liturgical calendar data requirements and seasonality use | Given the PAULUS Define liturgical calendar data requirements and seasonality use task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define liturgical calendar data requirements and seasonality use. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390k32
DU-01 | Review liturgical calendar data sources and cross-validators | Given the PAULUS Review liturgical calendar data sources and cross-validators task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Review liturgical calendar data sources and cross-validators. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390k61
SRC-01 | Prepare GCATHOLIC source mapping for liturgical calendar ingestion | Given the PAULUS Prepare GCATHOLIC source mapping for liturgical calendar ingestion task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Prepare GCATHOLIC source mapping for liturgical calendar ingestion. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d3bw6u5
SRC-02 | Prepare LITCAL source mapping for liturgical calendar ingestion | Given the PAULUS Prepare LITCAL source mapping for liturgical calendar ingestion task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Prepare LITCAL source mapping for liturgical calendar ingestion. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d3bw6v0
SRC-03 | Prepare ROMCAL source mapping for liturgical calendar ingestion | Given the PAULUS Prepare ROMCAL source mapping for liturgical calendar ingestion task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Prepare ROMCAL source mapping for liturgical calendar ingestion. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d3bw6vm
DP-01 | Build liturgical calendar data ingestion pipeline | Given the PAULUS Build liturgical calendar data ingestion pipeline task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build liturgical calendar data ingestion pipeline. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390k9n
MODEL-01 | Implement calendar validation and cross-check logic | Given the PAULUS Implement calendar validation and cross-check logic task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Implement calendar validation and cross-check logic. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390kb3
MODEL-02 | Program future calendar generation using pattern searching | Given the PAULUS Program future calendar generation using pattern searching task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Program future calendar generation using pattern searching. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d3bw6w2
DEP-01 | Load validated liturgical calendar data into database | Given the PAULUS Load validated liturgical calendar data into database task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Load validated liturgical calendar data into database. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390kn9
EVAL-01 | Validate liturgical calendar data accuracy | Given the PAULUS Validate liturgical calendar data accuracy task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate liturgical calendar data accuracy. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390kf6
MS-01 | Document liturgical calendar pipeline process | Given the PAULUS Document liturgical calendar pipeline process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document liturgical calendar pipeline process. | 0.4318% | planning/backlog | FALSE | https://app.clickup.com/t/86d390kpr
Total Accomplished |  |  |  | 4.75% |  | 0%
Task ID | WEATHER | Task Name | Weather Data Collection Pipeline |  | in progress |  | https://app.clickup.com/t/86d39pnnk
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
BUS-01 | Define weather data requirements and use in analytics | Given the PAULUS Define weather data requirements and use in analytics task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Define weather data requirements and use in analytics. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pntt
DU-01 | Review weather data sources and APIs | Given the PAULUS Review weather data sources and APIs task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Review weather data sources and APIs. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pnrf
EXT-01 | Extract weather data from selected source APIs or datasets | Given the PAULUS Extract weather data from selected source APIs or datasets task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Extract weather data from selected source APIs or datasets. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d3bw6tt
DP-01 | Build weather data ingestion pipeline | Given the PAULUS Build weather data ingestion pipeline task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Build weather data ingestion pipeline. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pnrg
MODEL-01 | Implement weather data validation and cross-check logic | Given the PAULUS Implement weather data validation and cross-check logic task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Implement weather data validation and cross-check logic. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pnrh
DEP-01 | Load validated weather data into database | Given the PAULUS Load validated weather data into database task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Load validated weather data into database. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pnta
EVAL-01 | Validate weather data accuracy and completeness | Given the PAULUS Validate weather data accuracy and completeness task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate weather data accuracy and completeness. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pntv
UAT-01 | Validate weather data pipeline with target users | Given the PAULUS Validate weather data pipeline with target users task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Validate weather data pipeline with target users. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pntd
MS-01 | Document weather data collection pipeline process | Given the PAULUS Document weather data collection pipeline process task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Document weather data collection pipeline process. | 0.5278% | planning/backlog | FALSE | https://app.clickup.com/t/86d39pntw
Total Accomplished |  |  |  | 4.75% |  | 0%
Module Accomplishment | MOD-ANA | Analytics, Models, and Decision Support |  | 28.5% |  | 0%

## CORE
Task ID | HOST | Task Name | Hosting and Deployment Setup |  | planning/backlog |  | https://app.clickup.com/t/86d38te3n
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
HOST | Hosting and Deployment Setup | Given the PAULUS Hosting and Deployment Setup task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Hosting and Deployment Setup. | 2.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38te3n
Total Accomplished |  |  |  | 2.75% |  | 0%
Task ID | UAT | Task Name | User Acceptance Testing and Final Validation |  | planning/backlog |  | https://app.clickup.com/t/86d38th2p
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
UAT | User Acceptance Testing and Final Validation | Given the PAULUS User Acceptance Testing and Final Validation task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for User Acceptance Testing and Final Validation. | 2.75% | planning/backlog | FALSE | https://app.clickup.com/t/86d38th2p
Total Accomplished |  |  |  | 2.75% |  | 0%
Module Accomplishment | CORE | Hosting, Repository, and Project Management |  | 5.5% |  | 0%

## MANUSCRIPT
Task ID | MS-01 | Task Name | Revise Chapter 3 methodology to Agile Kanban |  | in progress |  | https://app.clickup.com/t/86d391p3k
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-01 | Revise Chapter 3 methodology to Agile Kanban | Given the PAULUS Revise Chapter 3 methodology to Agile Kanban task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Revise Chapter 3 methodology to Agile Kanban. | 1.667% | in progress | FALSE | https://app.clickup.com/t/86d391p3k
Total Accomplished |  |  |  | 1.667% |  | 0%
Task ID | MS-02 | Task Name | Add Kanban literature in Chapter 2 |  | for qa / internal testing |  | https://app.clickup.com/t/86d391r9d
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-02 | Add Kanban literature in Chapter 2 | Given the PAULUS Add Kanban literature in Chapter 2 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Add Kanban literature in Chapter 2. | 1.667% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d391r9d
Total Accomplished |  |  |  | 1.667% |  | 0%
Task ID | MS-03 | Task Name | Add ClickUp tool discussion in Chapter 2 |  | for qa / internal testing |  | https://app.clickup.com/t/86d391rag
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-03 | Add ClickUp tool discussion in Chapter 2 | Given the PAULUS Add ClickUp tool discussion in Chapter 2 task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Add ClickUp tool discussion in Chapter 2. | 1.667% | for qa / internal testing | FALSE | https://app.clickup.com/t/86d391rag
Total Accomplished |  |  |  | 1.667% |  | 0%
Task ID | MS-04 | Task Name | Draft Chapter 4 results and testing discussion |  | planning/backlog |  | https://app.clickup.com/t/86d3921qu
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-04 | Draft Chapter 4 results and testing discussion | Given the PAULUS Draft Chapter 4 results and testing discussion task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Draft Chapter 4 results and testing discussion. | 1.667% | planning/backlog | FALSE | https://app.clickup.com/t/86d3921qu
Total Accomplished |  |  |  | 1.667% |  | 0%
Task ID | MS-05 | Task Name | Draft Chapter 5 conclusions and recommendations |  | planning/backlog |  | https://app.clickup.com/t/86d3921r5
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-05 | Draft Chapter 5 conclusions and recommendations | Given the PAULUS Draft Chapter 5 conclusions and recommendations task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Draft Chapter 5 conclusions and recommendations. | 1.667% | planning/backlog | FALSE | https://app.clickup.com/t/86d3921r5
Total Accomplished |  |  |  | 1.667% |  | 0%
Task ID | MS-06 | Task Name | Compile appendix materials and supporting evidence |  | planning/backlog |  | https://app.clickup.com/t/86d3921ru
Subtask ID | Subtask / Task Name | Acceptance Criteria | Evidence / Deliverable | Weight Allocation | ClickUp Status | Accepted | ClickUp URL
MS-06 | Compile appendix materials and supporting evidence | Given the PAULUS Compile appendix materials and supporting evidence task is implemented, the feature should meet the approved capstone requirements and pass review against its expected behavior. | ClickUp task evidence, implementation output, QA notes, screenshots, tests, or manuscript updates for Compile appendix materials and supporting evidence. | 1.667% | planning/backlog | FALSE | https://app.clickup.com/t/86d3921ru
Total Accomplished |  |  |  | 1.667% |  | 0%
Module Accomplishment | MANUSCRIPT | Manuscript and Documentation |  | 10% |  | 0%

## README
PAULUS Acceptance Criteria Tracker
Source | Built from ClickUp tasks under the PAULUS space fetched on 2026-06-15.
Structure | Workbook keeps the ClickUp module/task grouping and includes task URLs for traceability.
Accepted | Use the Accepted column to mark formal acceptance. ClickUp Status is preserved separately.
Formula | Actual accomplishment uses SUMIF over accepted TRUE values and task weight allocations.
Google Sheets | Formulas use SUM and SUMIF so they should import cleanly into Google Sheets.